## Introduction

NMIT is adopting a project management approach to manage flexible learning initiatives. The Flexible Learning Team has developed a project management toolkit to support this approach and these guidelines describe the rationale and processes involved.

Documents within the NMIT Flexible Learning Project Toolkit:

- These guidelines

- Flexible learning project proposal template

- Flexible learning project execution plan template

- Flexible learning course design plan template

- Good practice checklists – course design & content; online environment

- Style guide for online / blended courses

- Sample documents and courses demonstrating good practice in flexible learning design and development

## Rationale

A project management approach provides a framework to ensure clear objectives are set, responsibility and resources are appropriately allocated and the budget and project schedule are carefully managed. This framework is required for flexible learning initiatives because:

- NMIT has limited resources which must be allocated to initiatives that match our strategic objectives and current capabilities.

- NMIT is new to developing flexible learning courses and initiatives often involve the changes to existing teaching and support practices and processes that need to be carefully managed.

- Much of the flexible learning project work is focussed on course design and resource development which is not covered in detail within existing academic development processes.

- Development of flexible learning courses requires access to a wide range of expertise (technical, pedagogical, support services) that requires co-ordination to ensure everyone understands their role.

- Staff allocated responsibility for developing flexible learning courses usually require additional training in design processes, teaching strategies, technical capability and course management processes.

- Flexible learning courses require more design and resource development work to occur prior to course commencement than that allowed for in current programme development cycles.

## Links with academic quality processes

This process operates in parallel to the NMIT academic quality processes, although the two will of course feed into each other.

Flexible learning projects may be identified in the course of annual programme reviews or new programme development projects. Other flexible learning projects impacting course delivery may require changes to programme regulations that require academic approval. The standard concept plan outlining the proposed changes at programme or course level is usually the first step in gaining these approvals. The flexible learning project toolkit can be used to support the development of a concept plan and subsequent business case (or visa versa).

A change of teaching mode (e.g. from classroom based to distance delivery) must be approved by the NMIT academic approval structures and in some cases by an external body, depending on the course level and degree of change.

## Project management requirements

- Small projects – a simple expansion of the project proposal to include key milestones, plus communication and reporting processes.

- Major projects – complete a detailed execution plan based on the NMIT Flexible Learning project execution plan template.

The Project Execution Plan (PEP) is the core document for the management of a significant project. As well as defining the project objectives and schedules it is a statement of the policies and procedures defined by the project team, although usually developed by the project manager and the Flexible Learning Advisor for the project sponsor’s approval. It sets out in a structured format the project scope, objectives, relative priorities, roles and responsibilities and quality management processes.

The NMIT PEP template is designed as starting point, acting as a checklist of matters that should be considered in establishing a project.  It is not anticipated that every project manager will follow this format to the letter or necessarily include all the components in their final document.  The greater the complexity, risks, parties and time scales involved the closer to the full template the final execution plan will be.

In addition to standard project management components, the execution plan must detail processes for quality control checks required on course designs prior to development and final quality checks required prior to public release. The course design template, good practice checklists and style guide for online/blended courses are key components in this quality control process.